## Slide 1
M
J
E
B
C
D
F
G
H
I
K
L
Legend:
Process | Name of Process
A | Enter Info on dbClarity (1 day)
B | Initial Communications (5 days)
C | ID, Assess & Accept Dependencies (3 days)
D | Customer Focus Groups (6 days)
E | Requirements Gathering Workshop(s) (11 days)
F | Draft Initiation Management Plan (4 days)
G | Review Team Plan Allocation (2 days)
Process | Name of Process
H | Financial Planning & Reviews (7 days)
I | Create Financial Assessment (2 days + 1 day)
J | Approved Financial Assessment & Initiation Management Plan (4 days + 1 day)
K | Pre-Launch Communications (2 days)
L | System Development & Testing (35 days)
M | Training of Administration & Services (12 days)
N | Final Handover & Project Close (11 days)
A
Start
Stop
N
0|1|1
1|5|6
6|6|12
15|4|19
19|2|21
1|3|4
4|11|15
21|7|28
27|2|29
28|4|32
32|2|34
32|35|67
67|12|79
75|7|82
75|0|82
67|0|79
32|0|67
65|33|67
28|0|32
27|0|29
21|0|28
19|0|21
15|0|19
1|0|4
4|0|15
4|3|9
9|3|15
0|1|1